## Risks
HUrricane Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2025-04-10 | Time Management Issues | Underestimating time for coding, testing, or documentation. | I | 5 | 45% | 2.25 | Project Manager | Create a timeline with milestones; allocate buffer time for delays.
2 | 2025-04-10 | Team Coordination Problems | Miscommunication or uneven workload among team members. | I | 3 | 40% | 1.2 | Project Manager | Assign roles clearly; use tools like GitLab and hold regular check-ins.
3 | 2025-04-10 | Data Management Errors | Poor database design or lack of validation for mock data (e.g., category, orders). | D | 4 | 20% | 0.8 | Software Architect | Design simple schema early; test with sample data and add validation.
4 | 2025-04-10 | User Interface Issues | Confusing or unintuitive UI design (e.g., unclear buttons). | D | 3 | 25% | 0.75 | Software Analyst | Sketch wireframe; get early peer feedback and simplify design.
5 | 2025-04-10 | Scope Creep | Adding features beyond assignment requirements (e.g., payment options). | I | 4 | 30% | 1.2 | Software Confiuguration Manager | Define MVP based on assignment brief; avoid extra features unless time permits.
6 | 2025-04-10 | Functionality Bugs | Errors in core features. | D | 5 | 60% | 3 | Software Tester | Test features incrementally; prioritize fixing critical bugs.
7 | 2025-04-10 | Device Compatibility | App not working across browsers or devices. | D | 3 | 40% | 1.2 | Software Confiuguration Manager | Test on multiple platforms; use responsive design principles.
8 | 2025-04-10 | Documentation Shortfalls | Incomplete or unclear documentation ( code comments). | I | 2 | 20% | 0.4 | Software Analyst | Document as you go; include setup instructions and key decisions in a README.
9 | 2025-04-10 | Submission Risks | Issues during submission (e.g., file corruption, late upload). | I | 5 | 30% | 1.5 | Project Manager | Test submission process early; submit ahead of deadline.
10 | 2025-04-11 | Database Issues | Frequent connection timeouts and slow query performance due to suboptimal indexing and inefficient query design. | D | 3 | 50% | 1.5 | Software Architect | Review indexing strategy; optimize queries and adjust connection pooling parameters.
11 | 2025-04-11 | Demo Standard Accessibility Issue | The interface is unable to access the defined demo standards; this issue leads to disruptions in demo presentations and user experience. | D | 4 | 35% | 1.4 | Software Analyst | Review and update the configuration to comply with demo standards; integrate the relevant guideline documents.
12 | 2025-04-11 | Incomplete Use Cases for Demo Release | Critical use cases planned for the demo release are missing, leading to uncertainty in the application's workflow. | I | 4 | 30% | 1.2 | Software Analyst | Perform a comprehensive use case analysis; review requirements and update the demo documentation accordingly.
13 | 2025-04-11 | Inconsistent API Responses | API endpoints return data in varying formats, causing integration issues with the frontend. | D | 4 | 45% | 1.8 | Software Architect | Standardize API responses; implement response schema validation.
14 | 2025-04-11 | Ambiguous Requirement Specifications | Lack of clear specifications leads to differing interpretations among team members. | I | 3 | 35% | 1.05 | Project Manager | Conduct requirement clarification meetings; maintain a shared, updated specification document.
15 | 2025-04-11 | Inadequate Unit Testing Coverage | Many functions are untested, increasing the risk of undetected bugs in production. | D | 5 | 50% | 2.5 | Software Tester | Define testing criteria; enforce minimum coverage through CI pipelines.
16 | 2025-04-11 | Outdated Data Samples for Development | Developers rely on old and inaccurate mock data, leading to misrepresentative feature behavior. | D | 3 | 25% | 0.75 | Software Analyst | Regularly update sample data; sync with real use cases and ensure validity.
17 | 2025-04-11 | Version Control Conflicts | Merge conflicts frequently occur due to lack of branch discipline and unclear commit messages. | I | 4 | 40% | 1.6 | Software Configuration Manager | Define branching strategy; implement commit message guidelines and conflict resolution sessions.
18 | 2025-04-11 | Feature Deployment Delays | Features take longer than estimated due to unexpected technical complications and unclear task breakdowns. | I | 4 | 30% | 1.2 | Project Manager | Improve sprint planning accuracy; involve technical staff in estimation and risk assessment.
19 | 2025-04-11 | Missing Configuration Files in Repo | Essential environment configuration files are missing from the repository, causing delays during onboarding or deployment. | D | 3 | 20% | 0.6 | Software Configuration Manager | Include sample config files; document setup process and validate before commit.
20 | 2025-04-11 | Authentication Token Expiry Issues | Users are unexpectedly logged out due to short token expiry time without refresh logic. | D | 3 | 35% | 1.05 | Software Architect | Implement token refresh mechanism; update session handling policies for better user experience.
21 | 2025-04-11 | Untracked Design Changes | UI components were changed without updating wireframes or informing the dev team, causing implementation mismatches. | I | 3 | 25% | 0.75 | Software Analyst | Establish a UI change log; notify developers about updates and maintain wireframe version control.